CRS-PDVS Executive Brief Master Plan

Planning guide for the first government-facing executive brief

| Status | Confidential Internal Working Document |
| --- | --- |
| Prepared for | Institutional review and controlled circulation |
| Prepared under | CRS-PDVS programme documentation set |

Cross River State • Blue-White Service Design • Pensioner-Centred Modernisation

# 1. Document Purpose

This planning document governs the development of the first CRS-PDVS executive brief. It fixes the purpose, audience, structure, tone, evidence rules, and drafting sequence for the final ten-page paper to be presented for institutional consideration.

Its role is to prevent drift. The final brief must read as a disciplined public-service proposal: state-aware, pension-aware, legally conscious, and operationally realistic.

# 2. Core Objective of the Executive Brief

Present a concise and credible proposal for digital pensioner verification in Cross River State.

Show a sound understanding of pensioner welfare, administrative workflow, and fraud-control realities.

Reflect the state context: 18 local government areas, mixed urban-rural access conditions, and long travel distances from Calabar to northern LGAs.

Translate the idea into a phased implementation pathway rather than an all-at-once system replacement.

# 3. Audience Map

The brief must work for multiple readers at once. It should satisfy the Pension Board, senior civil servants, finance officials, digital-governance stakeholders, legal reviewers, and trusted advisers who may screen the document before it reaches executive level.

Primary readers: Pension Board leadership, Head of Service, Ministry of Finance, ICT and digital-governance stakeholders.

Secondary readers: legal reviewers, compliance officers, technical assessors, senior advisers, and programme gatekeepers.

# 4. What Smart Government Readers Will Test

Does the document understand the actual problem, or is it generic?

Does it respect existing administrative structures?

Is the tone sober and non-accusatory?

Does it show awareness of identity, biometric, and data-protection obligations?

Is the implementation pathway realistic and affordable at pilot stage?

Does it avoid overclaiming what software alone can fix?

# 5. Tone and Writing Rules

Use formal institutional English with short-to-medium sentences.

Avoid startup language, hype, sentimentality, or activist framing.

Use specific Cross River and Nigerian context where relevant.

Keep the document calm, implementation-focused, and respectful to existing public institutions.

# 6. Recommended 10-Page Structure

The final brief should follow a deliberate sequence that establishes legitimacy before solution detail. The preferred order is fixed below and should not be altered without reason.

## Page Architecture

| Reference point | Implication for CRS-PDVS |
| --- | --- |
| Page 1: Cover | Signal seriousness immediately with title, subtitle, confidentiality marking, and institutional purpose. |
| Page 2: Executive Summary | Provide a one-page understanding for senior readers who may not read the whole brief. |
| Pages 3-4: Context and Opportunity | Explain the human burden of manual verification and why a digital service is timely. |
| Pages 5-7: Solution and Public Value | Describe the product, how it works, and why it matters for pensioners and administration. |
| Pages 8-10: Governance, Roadmap and Ask | Address data protection, phased delivery, pilot logic, and a modest request for collaboration. |

# 7. Evidence Strategy

The executive brief should be evidence-guided rather than citation-heavy. It should rely first on official state publications and national regulatory materials, then use reputable contextual reporting only where needed to establish operational reality.

Cross River State official sources: demographics, LGA structure, budget documents, state public communications.

National sources: PenCom, NIMC, NDPA-era data governance material, and regulated identity-verification references.

Comparative sources: credible government-run digital life-certificate systems such as India’s Jeevan Pramaan.

# 8. Cross River-Specific Framing Requirements

The brief must demonstrate local understanding. Cross River is not a single-city operating environment. Administrative reach stretches from Calabar through central and northern LGAs, with significant variation in population density, travel burden, connectivity, and citizen support needs.

Acknowledge the 18-LGA structure and service-delivery spread.

Recognise Calabar as the administrative centre without writing as though all pensioners are near it.

Treat assisted verification as a necessity, not an optional add-on.

Use state-native but restrained language; the document should feel aligned with service delivery, not campaign messaging.

# 9. Drafting Workflow

Lock title, subtitle, and purpose before drafting.

Assemble evidence notes under state context, national pension context, data governance, and comparative models.

Draft the body first; write the executive summary last.

Compress for page economy without sacrificing clarity.

Run a final institutional-readability pass before release.

# 10. Expected Output Standard

The finished executive brief should leave one impression: this proposal is thoughtful, disciplined, respectful, and worth a serious stakeholder conversation.